## Intro
SISTESEG
AI AND CIBERSECURITY
2025

## Matriz de Controles
Item | Control | Dificultad | Fase | Descripción del Control | Tecnología | Documento | Actividad humana | Dias trabajo x Ingeniero
Controles Organizacionales (A.5)
1 | 5.1 | 3 | 2 | Policies for information security |  | x | x | 8
2 | 5.2 | 3 | 2 | Information security roles and responsibilities |  | x |  | 3
3 | 5.3 | 1 | 2 | Segregation of duties |  | x |  | 1
4 | 5.4 | 1 | 2 | Management responsibilities |  | x |  | 1
5 | 5.5 | 1 | 2 | Contact with authorities |  | x |  | 1
6 | 5.6 | 1 | 2 | Contact with special interest groups |  | x |  | 1
7 | 5.7 | 1 | 2 | Threat intelligence |  | x |  | 3
8 | 5.8 | 3 | 2 | Information security in project management |  | x |  | 3
9 | 5.9 | 3 | 2 | Inventory of information and other associated assets |  | x |  | 7
10 | 5.10 | 1 | 2 | Acceptable use of information and other associated assets |  | x |  | 1
11 | 5.11 | 1 | 2 | Return of assets |  | x |  | 1
12 | 5.12 | 3 | 2 | Classification of information |  | x |  | 7
13 | 5.13 | 1 | 2 | Labelling of information |  | x |  | 3
14 | 5.14 | 1 | 2 | Information transfer | x |  | x | 1
15 | 5.15 | 1 | 2 | Access control | x |  | x | 1
16 | 5.16 | 1 | 2 | Identity management | x |  | x | 1
17 | 5.17 | 1 | 2 | Authentication information | x |  | x | 1
18 | 5.18 | 1 | 2 | Access rights | x |  | x | 1
19 | 5.19 | 1 | 2 | Information security in supplier relationships |  | x |  | 3
20 | 5.20 | 1 | 2 | Addressing information security within supplier agreements |  | x |  | 2
21 | 5.21 | 1 | 2 | Managing information security in the ICT supply chain |  | x |  | 2
22 | 5.22 | 1 | 2 | Monitoring, review and change management of supplier services |  | x |  | 2
23 | 5.23 | 1 | 2 | Information security for use of cloud services |  | x |  | 2
24 | 5.24 | 3 | 2 | Information security incident management planning and preparation |  | x | x | 8
25 | 5.25 | 1 | 2 | Assessment and decision on information security events | x
26 | 5.26 | 1 | 2 | Response to information security incidents |  | x | x | 1
27 | 5.27 | 1 | 2 | Learning from information security incidents |  | x |  | 1
28 | 5.28 | 1 | 2 | Collection of evidence |  | x |  | 1
29 | 5.29 | 1 | 2 | Information security during disruption |  | x |  | 1
30 | 5.30 | 3 | 2 | ICT readiness for business continuity |  | x |  | 13
31 | 5.31 | 1 | 2 | Legal, statutory, regulatory and contractual requirements |  | x |  | 1
32 | 5.32 | 1 | 2 | Intellectual property rights |  | x |  | 1
33 | 5.33 | 1 | 2 | Protection of records |  | x |  | 1
34 | 5.34 | 1 | 2 | Privacy and protection of personal identifiable information (PII) |  | x |  | 1
35 | 5.35 | 1 | 2 | Independent review of information security |  | x |  | 1
36 | 5.36 | 1 | 2 | Compliance with policies, rules and standards for information security |  | x |  | 1
37 | 5.37 | 3 | 2 | Documented operating procedures |  | x |  | 8
|  |  |  | TOTAL DIAS |  |  |  | 95
Controles de Personal (A.6)
38 | 6.1 | 1 | 4 | Screening |  | x |  | 3
39 | 6.2 | 1 | 4 | Terms and conditions of employment |  | x |  | 1
40 | 6.3 | 3 | 1 | Information security awareness, education and training |  | x | x | 7
41 | 6.4 | 1 | 4 | Disciplinary process |  | x |  | 1
42 | 6.5 | 1 | 4 | Responsibilities after termination or change of employment |  | x |  | 1
43 | 6.6 | 1 | 4 | Confidentiality or non-disclosure agreements |  | x |  | 1
44 | 6.7 | 1 | 4 | Remote working |  | x |  | 1
45 | 6.8 | 1 | 4 | Information security event reporting |  | x |  | 1
|  |  |  | TOTAL DIAS |  |  |  | 16
Controles Físicos (A.7)
46 | 7.1 | 2 | 3 | Physical security perimeters | x
47 | 7.2 | 2 | 3 | Physical entry | x | x |  | 2
48 | 7.3 | 1 | 3 | Securing offices, rooms and facilities | x
49 | 7.4 | 2 | 3 | Physical security monitoring | x
50 | 7.5 | 1 | 3 | Protecting against physical and environmental threats | x
51 | 7.6 | 1 | 3 | Working in secure areas |  | x |  | 1
52 | 7.7 | 1 | 3 | Clear desk and clear screen |  | x |  | 1
53 | 7.8 | 1 | 3 | Equipment siting and protection |  | x |  | 1
54 | 7.9 | 1 | 3 | Security of assets off-premises | x
55 | 7.10 | 1 | 3 | Storage media | x
56 | 7.11 | 1 | 3 | Supporting utilities | x
57 | 7.12 | 1 | 3 | Cabling security | x
58 | 7.13 | 1 | 3 | Equipment maintenance | x
59 | 7.14 | 1 | 3 | Secure disposal or re-use of equipment |  | x |  | 1
|  |  |  | TOTAL DIAS |  |  |  | 6
Controles Tecnológicos (A.8)
60 | 8.1 | 1 | 2 | User end point devices |  | x |  | 1
61 | 8.2 | 1 | 2 | Privileged access rights |  | x |  | 1
62 | 8.3 | 1 | 2 | Information access restriction | x
63 | 8.4 | 1 | 2 | Access to source code | x
64 | 8.5 | 2 | 2 | Secure authentication | x
65 | 8.6 | 3 | 2 | Capacity management | x | x |  | 5
66 | 8.7 | 1 | 2 | Protection against malware | x
67 | 8.8 | 3 | 2 | Management of technical vulnerabilities | x | x |  | 5
68 | 8.9 | 3 | 2 | Configuration management |  | x |  | 5
69 | 8.10 | 1 | 2 | Information deletion | x
70 | 8.11 | 1 | 2 | Data masking | x
71 | 8.12 | 1 | 2 | Data leakage prevention | x
72 | 8.13 | 3 | 2 | Information backup | x | x |  | 4
73 | 8.14 | 3 | 2 | Redundancy of information processing facilities | x | x |  | 10
74 | 8.15 | 3 | 2 | Logging | x |  | x | 4
75 | 8.16 | 1 | 2 | Monitoring activities | x
76 | 8.17 | 1 | 2 | Clock synchronization | x
77 | 8.18 | 1 | 2 | Use of privileged utility programs |  | x |  | 1
78 | 8.19 | 1 | 2 | Installation of software on operational systems |  | x |  | 1
79 | 8.20 | 1 | 2 | Networks security | x | x |  | 2
80 | 8.21 | 1 | 2 | Security of network services | x
81 | 8.22 | 1 | 2 | Segregation of networks | x
82 | 8.23 | 1 | 2 | Web filtering | x
83 | 8.24 | 3 | 2 | Use of cryptography | x | x |  | 5
84 | 8.25 | 3 | 2 | Secure development life cycle |  | x |  | 7
85 | 8.26 | 1 | 2 | Application security requirements |  | x |  | 1
86 | 8.27 | 1 | 2 | Secure system architecture and engineering principles |  | x |  | 1
87 | 8.28 | 1 | 2 | Secure coding | x | X |  | 1
88 | 8.29 | 1 | 2 | Security testing in development and acceptance | x
89 | 8.30 | 1 | 2 | Outsourced development | x
90 | 8.31 | 1 | 2 | Separation of development, test and production environments |  | x |  | 1
91 | 8.32 | 3 | 2 | Change management |  | x |  | 7
92 | 8.33 | 1 | 2 | Test information |  | x |  | 1
93 | 8.34 | 1 | 2 | Protection of information systems during audit testing |  | x |  | 1
|  |  |  | TOTAL DIAS |  |  |  | 64
Clausulas
94 | 4 | 1 | 1 | Context of the organization |  | x |  | 4
95 | 5 | 1 | 1 | Leadership |  | x |  | 2
96 | 6 | 1 | 1 | Planning |  | x |  | 2
97 | 7 | 1 | 1 | Support |  | x |  | 2
98 | 8 | 3 | 1 | Operation (Risk) |  | x |  | 6
99 | 9 | 3 | 1 | Performance evaluation |  | x |  | 3
100 | 10 | 1 | 1 | Improvement |  | x |  | 2
|  |  |  | TOTAL DIAS |  |  |  | 17
[7 empty] | TOTAL DIAS | 198
[7 empty] | SEMANAS | 39.6
[7 empty] | MESES | 9.9

## Fase 1
Clausulas: enero-febrero
94 | 4 | 1 | 1 | Context of the organization | x | 4
95 | 5 | 1 | 1 | Leadership | x | 2
96 | 6 | 1 | 1 | Planning | x | 2
97 | 7 | 1 | 1 | Support | x | 2
98 | 8 | 3 | 1 | Operation (Risk) | x | 6
99 | 9 | 3 | 1 | Performance evaluation | x | 3
100 | 10 | 1 | 1 | Improvement | x | 2
|  |  |  | TOTAL DIAS |  | 17

## Fase 2
Controles Organizacionales (A.5): Febrero-Marzo-Abril
1 | 5.1 | 3 | 2 | Policies for information security |  | x | x | 8
2 | 5.2 | 3 | 2 | Information security roles and responsibilities |  | x |  | 3
3 | 5.3 | 1 | 2 | Segregation of duties |  | x |  | 1
4 | 5.4 | 1 | 2 | Management responsibilities |  | x |  | 1
5 | 5.5 | 1 | 2 | Contact with authorities |  | x |  | 1
6 | 5.6 | 1 | 2 | Contact with special interest groups |  | x |  | 1
7 | 5.7 | 1 | 2 | Threat intelligence |  | x |  | 3
8 | 5.8 | 3 | 2 | Information security in project management |  | x |  | 3
9 | 5.9 | 3 | 2 | Inventory of information and other associated assets |  | x |  | 7
10 | 5.10 | 1 | 2 | Acceptable use of information and other associated assets |  | x |  | 1
11 | 5.11 | 1 | 2 | Return of assets |  | x |  | 1
12 | 5.12 | 3 | 2 | Classification of information |  | x |  | 7
13 | 5.13 | 1 | 2 | Labelling of information |  | x |  | 3
14 | 5.14 | 1 | 2 | Information transfer | x |  | x | 1
15 | 5.15 | 1 | 2 | Access control | x |  | x | 1
16 | 5.16 | 1 | 2 | Identity management | x |  | x | 1
17 | 5.17 | 1 | 2 | Authentication information | x |  | x | 1
18 | 5.18 | 1 | 2 | Access rights | x |  | x | 1
19 | 5.19 | 1 | 2 | Information security in supplier relationships |  | x |  | 3
20 | 5.20 | 1 | 2 | Addressing information security within supplier agreements |  | x |  | 2
21 | 5.21 | 1 | 2 | Managing information security in the ICT supply chain |  | x |  | 2
22 | 5.22 | 1 | 2 | Monitoring, review and change management of supplier services |  | x |  | 2
23 | 5.23 | 1 | 2 | Information security for use of cloud services |  | x |  | 2
24 | 5.24 | 3 | 2 | Information security incident management planning and preparation |  | x | x | 8
25 | 5.25 | 1 | 2 | Assessment and decision on information security events | x
26 | 5.26 | 1 | 2 | Response to information security incidents |  | x | x | 1
27 | 5.27 | 1 | 2 | Learning from information security incidents |  | x |  | 1
28 | 5.28 | 1 | 2 | Collection of evidence |  | x |  | 1
29 | 5.29 | 1 | 2 | Information security during disruption |  | x |  | 1
30 | 5.30 | 3 | 2 | ICT readiness for business continuity |  | x |  | 13
31 | 5.31 | 1 | 2 | Legal, statutory, regulatory and contractual requirements |  | x |  | 1
32 | 5.32 | 1 | 2 | Intellectual property rights |  | x |  | 1
33 | 5.33 | 1 | 2 | Protection of records |  | x |  | 1
34 | 5.34 | 1 | 2 | Privacy and protection of personal identifiable information (PII) |  | x |  | 1
35 | 5.35 | 1 | 2 | Independent review of information security |  | x |  | 1
36 | 5.36 | 1 | 2 | Compliance with policies, rules and standards for information security |  | x |  | 1
37 | 5.37 | 3 | 2 | Documented operating procedures |  | x |  | 8
|  |  |  | TOTAL DIAS |  |  |  | 95

## Fase 3
Controles Tecnológicos (A.8): Abril-Junio
60 | 8.1 | 1 | 2 | User end point devices |  | x |  | 1
61 | 8.2 | 1 | 2 | Privileged access rights |  | x |  | 1
62 | 8.3 | 1 | 2 | Information access restriction | x
63 | 8.4 | 1 | 2 | Access to source code | x
64 | 8.5 | 2 | 2 | Secure authentication | x
65 | 8.6 | 3 | 2 | Capacity management | x | x |  | 5
66 | 8.7 | 1 | 2 | Protection against malware | x
67 | 8.8 | 3 | 2 | Management of technical vulnerabilities | x | x |  | 5
68 | 8.9 | 3 | 2 | Configuration management |  | x |  | 5
69 | 8.10 | 1 | 2 | Information deletion | x
70 | 8.11 | 1 | 2 | Data masking | x
71 | 8.12 | 1 | 2 | Data leakage prevention | x
72 | 8.13 | 3 | 2 | Information backup | x | x |  | 4
73 | 8.14 | 3 | 2 | Redundancy of information processing facilities | x | x |  | 10
74 | 8.15 | 3 | 2 | Logging | x |  | x | 4
75 | 8.16 | 1 | 2 | Monitoring activities | x
76 | 8.17 | 1 | 2 | Clock synchronization | x
77 | 8.18 | 1 | 2 | Use of privileged utility programs |  | x |  | 1
78 | 8.19 | 1 | 2 | Installation of software on operational systems |  | x |  | 1
79 | 8.20 | 1 | 2 | Networks security | x | x |  | 2
80 | 8.21 | 1 | 2 | Security of network services | x
81 | 8.22 | 1 | 2 | Segregation of networks | x
82 | 8.23 | 1 | 2 | Web filtering | x
83 | 8.24 | 3 | 2 | Use of cryptography | x | x |  | 5
84 | 8.25 | 3 | 2 | Secure development life cycle |  | x |  | 7
85 | 8.26 | 1 | 2 | Application security requirements |  | x |  | 1
86 | 8.27 | 1 | 2 | Secure system architecture and engineering principles |  | x |  | 1
87 | 8.28 | 1 | 2 | Secure coding | x | X |  | 1
88 | 8.29 | 1 | 2 | Security testing in development and acceptance | x
89 | 8.30 | 1 | 2 | Outsourced development | x
90 | 8.31 | 1 | 2 | Separation of development, test and production environments |  | x |  | 1
91 | 8.32 | 3 | 2 | Change management |  | x |  | 7
92 | 8.33 | 1 | 2 | Test information |  | x |  | 1
93 | 8.34 | 1 | 2 | Protection of information systems during audit testing |  | x |  | 1
|  |  |  | TOTAL DIAS |  |  |  | 64

## Fase 4
Controles Físicos (A.7): Junio
46 | 7.1 | 2 | 3 | Physical security perimeters | x
47 | 7.2 | 2 | 3 | Physical entry | x | x | 2
48 | 7.3 | 1 | 3 | Securing offices, rooms and facilities | x
49 | 7.4 | 2 | 3 | Physical security monitoring | x
50 | 7.5 | 1 | 3 | Protecting against physical and environmental threats | x
51 | 7.6 | 1 | 3 | Working in secure areas |  | x | 1
52 | 7.7 | 1 | 3 | Clear desk and clear screen |  | x | 1
53 | 7.8 | 1 | 3 | Equipment siting and protection |  | x | 1
54 | 7.9 | 1 | 3 | Security of assets off-premises | x
55 | 7.10 | 1 | 3 | Storage media | x
56 | 7.11 | 1 | 3 | Supporting utilities | x
57 | 7.12 | 1 | 3 | Cabling security | x
58 | 7.13 | 1 | 3 | Equipment maintenance | x
59 | 7.14 | 1 | 3 | Secure disposal or re-use of equipment |  | x | 1
|  |  |  | TOTAL DIAS |  |  | 6

## Fase 5
Controles de Personal (A.6): Julio
38 | 6.1 | 1 | 4 | Screening | x |  | 3
39 | 6.2 | 1 | 4 | Terms and conditions of employment | x |  | 1
40 | 6.3 | 3 | 1 | Information security awareness, education and training | x | x | 7
41 | 6.4 | 1 | 4 | Disciplinary process | x |  | 1
42 | 6.5 | 1 | 4 | Responsibilities after termination or change of employment | x |  | 1
43 | 6.6 | 1 | 4 | Confidentiality or non-disclosure agreements | x |  | 1
44 | 6.7 | 1 | 4 | Remote working | x |  | 1
45 | 6.8 | 1 | 4 | Information security event reporting | x |  | 1
|  |  |  | TOTAL DIAS |  |  | 16

## Avances
Item | Control | Dificultad | Fase | Descripción del Control | Avance | Fecha inicio | Fecha final | Observaciones
Controles Organizacionales
1 | 5.1 | 3 | 1 | Policies for information security | 0 | 2025-02-01 | 2025-07-01
2 | 5.2 | 3 | 1 | Information security roles and responsibilities | 2 | 2025-02-01 | 2025-07-01
3 | 5.3 | 1 | 1 | Segregation of duties | 0 | 2025-02-01 | 2025-07-01
4 | 5.4 | 1 | 1 | Management responsibilities | 0 | 2025-02-01 | 2025-07-01
5 | 5.5 | 1 | 5 | Contact with authorities | 0 | 2025-02-01 | 2025-07-01
6 | 5.6 | 1 | 5 | Contact with special interest groups | 3 | 2025-02-01 | 2025-07-01
7 | 5.7 | 1 | 5 | Threat intelligence | 0 | 2025-02-01 | 2025-07-01
8 | 5.8 | 3 | 5 | Information security in project management | 0 | 2025-02-01 | 2025-07-01
9 | 5.9 | 3 | 1 | Inventory of information and other associated assets | 1 | 2025-02-01 | 2025-07-01
10 | 5.10 | 1 | 5 | Acceptable use of information and other associated assets | 0 | 2025-02-01 | 2025-07-01
11 | 5.11 | 1 | 5 | Return of assets | 0 | 2025-02-01 | 2025-07-01
12 | 5.12 | 3 | 1 | Classification of information | 5 | 2025-02-01 | 2025-07-01
13 | 5.13 | 1 | 1 | Labelling of information | 0 | 2025-02-01 | 2025-07-01
14 | 5.14 | 1 | 5 | Information transfer | 0 | 2025-02-01 | 2025-07-01
15 | 5.15 | 1 | 1 | Access control | 0 | 2025-02-01 | 2025-07-01
16 | 5.16 | 1 | 1 | Identity management | 2 | 2025-02-01 | 2025-07-01
17 | 5.17 | 1 | 1 | Authentication information | 0 | 2025-02-01 | 2025-07-01
18 | 5.18 | 1 | 1 | Access rights | 0 | 2025-02-01 | 2025-07-01
19 | 5.19 | 1 | 5 | Information security in supplier relationships | 0 | 2025-02-01 | 2025-07-01
20 | 5.20 | 1 | 5 | Addressing information security within supplier agreements | 5 | 2025-02-01 | 2025-07-01
21 | 5.21 | 1 | 5 | Managing information security in the ICT supply chain | 0 | 2025-02-01 | 2025-07-01
22 | 5.22 | 1 | 5 | Monitoring, review and change management of supplier services | 0 | 2025-02-01 | 2025-07-01
23 | 5.23 | 1 | 5 | Information security for use of cloud services | 0 | 2025-02-01 | 2025-07-01
24 | 5.24 | 3 | 5 | Information security incident management planning and preparation | 0 | 2025-02-01 | 2025-07-01
25 | 5.25 | 1 | 5 | Assessment and decision on information security events | 0 | 2025-02-01 | 2025-07-01
26 | 5.26 | 1 | 5 | Response to information security incidents | 0 | 2025-02-01 | 2025-07-01
27 | 5.27 | 1 | 5 | Learning from information security incidents | 0 | 2025-02-01 | 2025-07-01
28 | 5.28 | 1 | 5 | Collection of evidence | 5 | 2025-02-01 | 2025-07-01
29 | 5.29 | 1 | 5 | Information security during disruption | 0 | 2025-02-01 | 2025-07-01
30 | 5.30 | 3 | 5 | ICT readiness for business continuity | 0 | 2025-02-01 | 2025-07-01
31 | 5.31 | 1 | 5 | Legal, statutory, regulatory and contractual requirements | 0 | 2025-02-01 | 2025-07-01
32 | 5.32 | 1 | 5 | Intellectual property rights | 5 | 2025-02-01 | 2025-07-01
33 | 5.33 | 1 | 5 | Protection of records | 0 | 2025-02-01 | 2025-07-01
34 | 5.34 | 1 | 5 | Privacy and protection of personal identifiable information (PII) | 0 | 2025-02-01 | 2025-07-01
35 | 5.35 | 1 | 5 | Independent review of information security | 0 | 2025-02-01 | 2025-07-01
36 | 5.36 | 1 | 5 | Compliance with policies, rules and standards for information security | 0 | 2025-02-01 | 2025-07-01
37 | 5.37 | 3 | 5 | Documented operating procedures | 0 | 2025-02-01 | 2025-07-01
Controles de Personal
38 | 6.1 | 1 | 4 | Screening | 1 | 2025-02-01 | 2025-07-01
39 | 6.2 | 1 | 4 | Terms and conditions of employment | 0 | 2025-02-01 | 2025-07-01
40 | 6.3 | 3 | 1 | Information security awareness, education and training | 0 | 2025-02-01 | 2025-07-01
41 | 6.4 | 1 | 4 | Disciplinary process | 1 | 2025-02-01 | 2025-07-01
42 | 6.5 | 1 | 4 | Responsibilities after termination or change of employment | 0 | 2025-02-01 | 2025-07-01
43 | 6.6 | 1 | 4 | Confidentiality or non-disclosure agreements | 3 | 2025-02-01 | 2025-07-01
44 | 6.7 | 1 | 4 | Remote working | 5 | 2025-02-01 | 2025-07-01
45 | 6.8 | 1 | 4 | Information security event reporting | 0 | 2025-02-01 | 2025-07-01
Controles Físicos
46 | 7.1 | 2 | 3 | Physical security perimeters | 0 | 2025-02-01 | 2025-07-01
47 | 7.2 | 2 | 3 | Physical entry | 0 | 2025-02-01 | 2025-07-01
48 | 7.3 | 1 | 3 | Securing offices, rooms and facilities | 0 | 2025-02-01 | 2025-07-01
49 | 7.4 | 2 | 3 | Physical security monitoring | 0 | 2025-02-01 | 2025-07-01
50 | 7.5 | 1 | 3 | Protecting against physical and environmental threats | 3 | 2025-02-01 | 2025-07-01
51 | 7.6 | 1 | 3 | Working in secure areas | 0 | 2025-02-01 | 2025-07-01
52 | 7.7 | 1 | 3 | Clear desk and clear screen | 0 | 2025-02-01 | 2025-07-01
53 | 7.8 | 1 | 3 | Equipment siting and protection | 0 | 2025-02-01 | 2025-07-01
54 | 7.9 | 1 | 3 | Security of assets off-premises | 0 | 2025-02-01 | 2025-07-01
55 | 7.10 | 1 | 3 | Storage media | 0 | 2025-02-01 | 2025-07-01
56 | 7.11 | 1 | 3 | Supporting utilities | 3 | 2025-02-01 | 2025-07-01
57 | 7.12 | 1 | 3 | Cabling security | 1 | 2025-02-01 | 2025-07-01
58 | 7.13 | 1 | 3 | Equipment maintenance | 0 | 2025-02-01 | 2025-07-01
59 | 7.14 | 1 | 3 | Secure disposal or re-use of equipment | 0 | 2025-02-01 | 2025-07-01
Controles Tecnológicos
60 | 8.1 | 1 | 2 | User end point devices | 0 | 2025-02-01 | 2025-07-01
61 | 8.2 | 1 | 2 | Privileged access rights | 0 | 2025-02-01 | 2025-07-01
62 | 8.3 | 1 | 2 | Information access restriction | 0 | 2025-02-01 | 2025-07-01
63 | 8.4 | 1 | 2 | Access to source code | 0 | 2025-02-01 | 2025-07-01
64 | 8.5 | 2 | 2 | Secure authentication | 0 | 2025-02-01 | 2025-07-01
65 | 8.6 | 3 | 2 | Capacity management | 2 | 2025-02-01 | 2025-07-01
66 | 8.7 | 1 | 2 | Protection against malware | 0 | 2025-02-01 | 2025-07-01
67 | 8.8 | 3 | 2 | Management of technical vulnerabilities | 1 | 2025-02-01 | 2025-07-01
68 | 8.9 | 3 | 2 | Configuration management | 0 | 2025-02-01 | 2025-07-01
69 | 8.10 | 1 | 2 | Information deletion | 5 | 2025-02-01 | 2025-07-01
70 | 8.11 | 1 | 2 | Data masking | 0 | 2025-02-01 | 2025-07-01
71 | 8.12 | 1 | 2 | Data leakage prevention | 0 | 2025-02-01 | 2025-07-01
72 | 8.13 | 3 | 2 | Information backup | 2 | 2025-02-01 | 2025-07-01
73 | 8.14 | 3 | 2 | Redundancy of information processing facilities | 2 | 2025-02-01 | 2025-07-01
74 | 8.15 | 3 | 2 | Logging | 2 | 2025-02-01 | 2025-07-01
75 | 8.16 | 1 | 2 | Monitoring activities | 2 | 2025-02-01 | 2025-07-01
76 | 8.17 | 1 | 2 | Clock synchronization | 2 | 2025-02-01 | 2025-07-01
77 | 8.18 | 1 | 2 | Use of privileged utility programs | 2 | 2025-02-01 | 2025-07-01
78 | 8.19 | 1 | 2 | Installation of software on operational systems | 2 | 2025-02-01 | 2025-07-01
79 | 8.20 | 1 | 2 | Networks security | 2 | 2025-02-01 | 2025-07-01
80 | 8.21 | 1 | 2 | Security of network services | 2 | 2025-02-01 | 2025-07-01
81 | 8.22 | 1 | 2 | Segregation of networks | 2 | 2025-02-01 | 2025-07-01
82 | 8.23 | 1 | 2 | Web filtering | 2 | 2025-02-01 | 2025-07-01
83 | 8.24 | 3 | 2 | Use of cryptography | 2 | 2025-02-01 | 2025-07-01
84 | 8.25 | 3 | 3 | Secure development life cycle | 2 | 2025-02-01 | 2025-07-01
85 | 8.26 | 1 | 3 | Application security requirements | 2 | 2025-02-01 | 2025-07-01
86 | 8.27 | 1 | 3 | Secure system architecture and engineering principles | 2 | 2025-02-01 | 2025-07-01
87 | 8.28 | 1 | 3 | Secure coding | 0 | 2025-02-01 | 2025-07-01
88 | 8.29 | 1 | 3 | Security testing in development and acceptance | 0 | 2025-02-01 | 2025-07-01
89 | 8.30 | 1 | 2 | Outsourced development | 1 | 2025-02-01 | 2025-07-01
90 | 8.31 | 1 | 3 | Separation of development, test and production environments | 0 | 2025-02-01 | 2025-07-01
91 | 8.32 | 3 | 2 | Change management | 0 | 2025-02-01 | 2025-07-01
92 | 8.33 | 1 | 2 | Test information | 0 | 2025-02-01 | 2025-07-01
93 | 8.34 | 1 | 2 | Protection of information systems during audit testing | 0 | 2025-02-01 | 2025-07-01
Clausulas
94 | 4 | 1 | 1 | Context of the organization | 2 | 2025-02-01 | 2025-07-01
95 | 5 | 1 | 1 | Leadership | 2 | 2025-02-01 | 2025-07-01
96 | 6 | 1 | 1 | Planning | 2 | 2025-02-01 | 2025-07-01
97 | 7 | 1 | 1 | Support | 5 | 2025-02-01 | 2025-07-01
98 | 8 | 3 | 1 | Operation (Risk) | 2 | 2025-02-01 | 2025-07-01
99 | 9 | 3 | 1 | Performance evaluation | 1 | 2025-02-01 | 2025-07-01
100 | 10 | 1 | 1 | Improvement | 2 | 2025-02-01 | 2025-07-01

## Cronograma I
FASE | Cronograma 2025 | Enero | Febrero | Marzo | Abril | Mayo | Junio | Julio
1 | Clausulas
2 | Controles organizacionales
3 | controles tecnologicos
4 | Controles fisicos
5 | Factor humano

## Cronograma II
Item | Control | Dificultad | Fase | Descripción del Control | Tecnología | Documento | Actividad humana | Dias trabajo x Ingeniero
Controles Organizacionales (A.5) | [8 empty] | Enero | Febrero | Marzo | Abril | Mayo | Junio | Julio
1 | 5.1 | 3 | 1 | Policies for information security |  | x | x | 8
2 | 5.2 | 3 | 1 | Information security roles and responsibilities |  | x |  | 3
3 | 5.3 | 1 | 2 | Segregation of duties |  | x |  | 1
4 | 5.4 | 1 | 1 | Management responsibilities |  | x |  | 1
5 | 5.5 | 1 | 2 | Contact with authorities |  | x |  | 1
6 | 5.6 | 1 | 2 | Contact with special interest groups |  | x |  | 1
7 | 5.7 | 1 | 2 | Threat intelligence |  | x |  | 3
8 | 5.8 | 3 | 2 | Information security in project management |  | x |  | 3
9 | 5.9 | 3 | 2 | Inventory of information and other associated assets |  | x |  | 7
10 | 5.10 | 1 | 2 | Acceptable use of information and other associated assets |  | x |  | 1
11 | 5.11 | 1 | 2 | Return of assets |  | x |  | 1
12 | 5.12 | 3 | 2 | Classification of information |  | x |  | 7
13 | 5.13 | 1 | 2 | Labelling of information |  | x |  | 3
14 | 5.14 | 1 | 2 | Information transfer | x |  | x | 1
15 | 5.15 | 1 | 2 | Access control | x |  | x | 1
16 | 5.16 | 1 | 2 | Identity management | x |  | x | 1
17 | 5.17 | 1 | 2 | Authentication information | x |  | x | 1
18 | 5.18 | 1 | 2 | Access rights | x |  | x | 1
19 | 5.19 | 1 | 2 | Information security in supplier relationships |  | x |  | 3
20 | 5.20 | 1 | 2 | Addressing information security within supplier agreements |  | x |  | 2
21 | 5.21 | 1 | 2 | Managing information security in the ICT supply chain |  | x |  | 2
22 | 5.22 | 1 | 2 | Monitoring, review and change management of supplier services |  | x |  | 2
23 | 5.23 | 1 | 2 | Information security for use of cloud services |  | x |  | 2
24 | 5.24 | 3 | 2 | Information security incident management planning and preparation |  | x | x | 8
25 | 5.25 | 1 | 2 | Assessment and decision on information security events | x
26 | 5.26 | 1 | 2 | Response to information security incidents |  | x | x | 1
27 | 5.27 | 1 | 2 | Learning from information security incidents |  | x |  | 1
28 | 5.28 | 1 | 2 | Collection of evidence |  | x |  | 1
29 | 5.29 | 1 | 2 | Information security during disruption |  | x |  | 1
30 | 5.30 | 3 | 2 | ICT readiness for business continuity |  | x |  | 13
31 | 5.31 | 1 | 2 | Legal, statutory, regulatory and contractual requirements |  | x |  | 1
32 | 5.32 | 1 | 2 | Intellectual property rights |  | x |  | 1
33 | 5.33 | 1 | 2 | Protection of records |  | x |  | 1
34 | 5.34 | 1 | 2 | Privacy and protection of personal identifiable information (PII) |  | x |  | 1
35 | 5.35 | 1 | 2 | Independent review of information security |  | x |  | 1
36 | 5.36 | 1 | 2 | Compliance with policies, rules and standards for information security |  | x |  | 1
37 | 5.37 | 3 | 2 | Documented operating procedures |  | x |  | 8
|  |  |  | TOTAL DIAS |  |  |  | 95
Controles de Personal (A.6)
38 | 6.1 | 1 | 4 | Screening |  | x |  | 3
39 | 6.2 | 1 | 4 | Terms and conditions of employment |  | x |  | 1
40 | 6.3 | 3 | 1 | Information security awareness, education and training |  | x | x | 7
41 | 6.4 | 1 | 4 | Disciplinary process |  | x |  | 1
42 | 6.5 | 1 | 4 | Responsibilities after termination or change of employment |  | x |  | 1
43 | 6.6 | 1 | 4 | Confidentiality or non-disclosure agreements |  | x |  | 1
44 | 6.7 | 1 | 4 | Remote working |  | x |  | 1
45 | 6.8 | 1 | 4 | Information security event reporting |  | x |  | 1
|  |  |  | TOTAL DIAS |  |  |  | 16
Controles Físicos (A.7)
46 | 7.1 | 2 | 3 | Physical security perimeters | x
47 | 7.2 | 2 | 3 | Physical entry | x | x |  | 2
48 | 7.3 | 1 | 3 | Securing offices, rooms and facilities | x
49 | 7.4 | 2 | 3 | Physical security monitoring | x
50 | 7.5 | 1 | 3 | Protecting against physical and environmental threats | x
51 | 7.6 | 1 | 3 | Working in secure areas |  | x |  | 1
52 | 7.7 | 1 | 3 | Clear desk and clear screen |  | x |  | 1
53 | 7.8 | 1 | 3 | Equipment siting and protection |  | x |  | 1
54 | 7.9 | 1 | 3 | Security of assets off-premises | x
55 | 7.10 | 1 | 3 | Storage media | x
56 | 7.11 | 1 | 3 | Supporting utilities | x
57 | 7.12 | 1 | 3 | Cabling security | x
58 | 7.13 | 1 | 3 | Equipment maintenance | x
59 | 7.14 | 1 | 3 | Secure disposal or re-use of equipment |  | x |  | 1
|  |  |  | TOTAL DIAS |  |  |  | 6
Controles Tecnológicos (A.8)
60 | 8.1 | 1 | 2 | User end point devices |  | x |  | 1
61 | 8.2 | 1 | 2 | Privileged access rights |  | x |  | 1
62 | 8.3 | 1 | 2 | Information access restriction | x
63 | 8.4 | 1 | 2 | Access to source code | x
64 | 8.5 | 2 | 2 | Secure authentication | x
65 | 8.6 | 3 | 2 | Capacity management | x | x |  | 5
66 | 8.7 | 1 | 2 | Protection against malware | x
67 | 8.8 | 3 | 2 | Management of technical vulnerabilities | x | x |  | 5
68 | 8.9 | 3 | 2 | Configuration management |  | x |  | 5
69 | 8.10 | 1 | 2 | Information deletion | x
70 | 8.11 | 1 | 2 | Data masking | x
71 | 8.12 | 1 | 2 | Data leakage prevention | x
72 | 8.13 | 3 | 2 | Information backup | x | x |  | 4
73 | 8.14 | 3 | 2 | Redundancy of information processing facilities | x | x |  | 10
74 | 8.15 | 3 | 2 | Logging | x |  | x | 4
75 | 8.16 | 1 | 2 | Monitoring activities | x
76 | 8.17 | 1 | 2 | Clock synchronization | x
77 | 8.18 | 1 | 2 | Use of privileged utility programs |  | x |  | 1
78 | 8.19 | 1 | 2 | Installation of software on operational systems |  | x |  | 1
79 | 8.20 | 1 | 2 | Networks security | x | x |  | 2
80 | 8.21 | 1 | 2 | Security of network services | x
81 | 8.22 | 1 | 2 | Segregation of networks | x
82 | 8.23 | 1 | 2 | Web filtering | x
83 | 8.24 | 3 | 2 | Use of cryptography | x | x |  | 5
84 | 8.25 | 3 | 2 | Secure development life cycle |  | x |  | 7
85 | 8.26 | 1 | 2 | Application security requirements |  | x |  | 1
86 | 8.27 | 1 | 2 | Secure system architecture and engineering principles |  | x |  | 1
87 | 8.28 | 1 | 2 | Secure coding | x | X |  | 1
88 | 8.29 | 1 | 2 | Security testing in development and acceptance | x
89 | 8.30 | 1 | 2 | Outsourced development | x
90 | 8.31 | 1 | 2 | Separation of development, test and production environments |  | x |  | 1
91 | 8.32 | 3 | 2 | Change management |  | x |  | 7
92 | 8.33 | 1 | 2 | Test information |  | x |  | 1
93 | 8.34 | 1 | 2 | Protection of information systems during audit testing |  | x |  | 1
|  |  |  | TOTAL DIAS |  |  |  | 64
Clausulas
94 | 4 | 1 | 1 | Context of the organization |  | x |  | 4
95 | 5 | 1 | 1 | Leadership |  | x |  | 2
96 | 6 | 1 | 1 | Planning |  | x |  | 2
97 | 7 | 1 | 1 | Support |  | x |  | 2
98 | 8 | 3 | 1 | Operation (Risk) |  | x |  | 6
99 | 9 | 3 | 1 | Performance evaluation |  | x |  | 3
100 | 10 | 1 | 1 | Improvement |  | x |  | 2
|  |  |  | TOTAL DIAS |  |  |  | 17